New voluntary service for parents Consultation approach

The department is leading the consultation process to design a new, voluntary service that supports parents who care for young children. The new service will be for parents who receive a Parenting Payment. It will help them to:

- plan for their future education and employment goals

- build their capabilities and skills

- work toward the type of paid work they want, when they’re ready.

We will work in partnership with key agencies and community organisations to undertake a multi-pronged engagement approach.

The engagement will be iterative with consultations running simultaneously to ensure we capture a range of perspectives and design ideas across our stakeholders in a limited timeframe.

# The approach has four phases

| Pre-Design | Design | Check-In and Early Direction | Design Options |
| --- | --- | --- | --- |
| May-June | Jul-Aug | Aug | Aug-Sept |
| We have sought people’s input to what our consultation should look like, and how our stakeholders prefer to participate. | Consult and collaborate to understand parents’ needs and goals, and the kind of supports we could provide. | Check-in with people about what we’ve learned, present our thoughts on what design could look like and get their feedback and advice. | We’ll come back to people to talk about options, and seek their feedback and advice to inform our decisions |

# Who are we talking to?

We are talking to a range of stakeholders relevant to this process, beginning with parents. Each stakeholder stream has a targeted approach of engagement. Engagement across stakeholder groups will occur concurrently, both directly and in partnership with community organisations.

| Past and Present Participants | First Nations | People with Disability | Migrant and Refugee |
| --- | --- | --- | --- |
| Youth | Women at risk | Community Groups | Peaks |
| Providers | Employers | Public |  |

## Past and present participants (survey and workshops with past and present participants)

Note: all locations are subject to confirmation and change, depending on take-up of invitations to workshops and confirmation of venues

| Who | How | When |
| --- | --- | --- |
| DEWR – Applied Behavioural Insights team | Call out survey and phone call inviting past and present ParentsNext participants to participate in workshops. | Early July |
| DEWR – Applied Behavioural Insights team | Phase 2 workshops with volunteer past and present ParentsNext participants: - Bankstown NSW - Brisbane QLD - Virtual | July |
| DEWR – Applied Behavioural Insights team (in consultation with Services Australia) | Phase 3 survey of past and present ParentsNext participants to test options and seek feedback on consultations. | August |
| DEWR – Applied Behavioural Insights team | Phase 4 workshops with volunteer past and present ParentsNext participants - Perth WA - Hobart TAS - Virtual | August/September |

## Potential participants (workshop with parenting payment recipients)

Note: all locations are subject to confirmation and change, depending on take-up of invitations to workshops and confirmation of venues.

| Who | How | When |
| --- | --- | --- |
| Services Australia | SMS/Email/Phone call inviting Parenting Payment recipients to participate in workshops. | July |
| Services Australia | - Phase 2 workshops with volunteer Parenting Payment participants: - Melbourne VIC - Toowoomba QLD - Canberra ACT | July |
| DEWR – Applied Behavioural Insights team | Phase 3 survey of participants to test options and seek feedback on consultations. | August |

## Targeted workshops with lived experience in key locations 
(face to face and virtual)

Note: all locations are subject to confirmation and change, depending on take-up of invitations to workshops and confirmation of venues.

| Cohorts | How | Locations | When |
| --- | --- | --- | --- |
| Women | Partnership with community organisations | Sydney/regional NSW Brisbane/regional QLD Adelaide/regional SA Shepparton VIC | July/August |
| First Nations | Specialist First Nations Facilitator Partnership with community organisation | Tamworth NSW Blacktown NSW Perth WA Yarrabah QLD Cairns QLD | July/August |
| Migrant and Refugee | Partnership with community organisation | Adelaide SA Mirrabooka WA Prahran VIC Logan Central QLD Blacktown NSW | July/August |
| People with Disability | Partnership with community organisation | Sydney/regional NSW Brisbane/regional QLD Adelaide/regional SA Melbourne/regional VIC | July/August |
| Youth | Partnership with community organisation | Burnie TAS Newcastle NSW Geelong VIC Corio VIC Virtual | July/August |
|  | Collaboration with Office for Youth | Virtual | July/August |

#### Community Groups, Peaks, Other

Relevant and representative community groups identified through previous submissions to the ParentsNext Inquiry and broad stakeholder analysis of high interest groups and individuals.

Pre-design discussions held with community and advocacy groups.

Testing of consultation approach and scope and framing of discussion topics and questions.

Targeted small procurement to support co-facilitation with trusted community partners for direct public participation in co-design.

Options feedback presented via community group and direct contact with participants (if they indicate they would like to receive follow-up information).

Roundtables with peaks, academics, service deliverers.

## Businesses

| Who | How | When |
| --- | --- | --- |
| DEWR - National Workforce Solutions Branch | Virtual outreach through Employment Liaison Officers; meetings with Industry peaks | July - August |

## Providers

| Who | How | When |
| --- | --- | --- |
| Employment Services peak bodies | Early meetings for feedback in developing consultation approach | June |
| Employment Services peak bodies | - Feedback on all consultations and options, virtual roundtables | July - August |
| Current ParentsNext Providers | Feedback on all consultations and options | 29 August, Workforce Australia National Forum |

## State and Territory Government

| Who | How | When |
| --- | --- | --- |
| State and Territory Government Representatives | Information sharing | July - August |